## Hexarule
[5 empty] | OEG Enhancement Request Tracker | [8 empty] | Hex-9999 Version No. 1.0
Project Name |  |  |  | BI Data Modernization | Track Name: |  | INFAGEN |  |  | PM Name
Request ID | Type (Bug or Enhan.) | Owner | Module/ Component | Description of the Reqeust | Request Date | Priority | Complexity | IAD Completed Date | IAD Sign-off Date | Estimated Effort (Hours) | Planned Closure Date | Actual Closure Date | Status | Discussion Notes/ Remarks
SR_01 | Enhancement | Snehasis | INFAGEN | Create new Tab for bulk DOWNLOADs and UPLOADs | 2015-11-26 | Medium |  |  |  | 40 | 2015-12-07 | 2015-12-16 | Completed
SR_02 | Enhancement | Snehasis | INFAGEN | Remove Download and Upload button From Review N Generate Page | 2015-11-26 | Medium |  |  |  | 2 | 2015-11-26 | 2015-12-16 | Completed
SR_03 | Bug | Venkat | INFAGEN | New template created via "Create Template" is not creating the XML while submitting from"Review&Generate". | 2015-11-26 | Medium |  |  |  | 16 | 2015-11-30 |  | Completed
SR_04 | Enhancement | Venkat | INFAGEN | Automatic Workflow creation | 2015-11-26 | Medium | [6 empty] | Completed
SR_05 | Enhancement | Venkat | Hexarule | Converting Hexarule .net to java | 2016-01-04 | Medium |  |  |  | 40 | 2016-01-22 | 2016-01-22 | Completed
SR_06 | Enhancement | Muthu | Profiler | MVC Conversion | 2015-12-23 | Medium |  |  |  | 42 | 2016-01-12 | 2016-01-12 | Completed
SR_07 | Enhancement | Nandha/Suresh | DASEM | New tool Development in MVC Frameowrk | 2015-12-18 | High | Medium |  |  | 44 | 2016-01-22 |  | In Build Phase
SR_08 | Enhancement | Jeyachithra | POC | Adding Conditional split in Automaton | 2016-01-06 | High |  |  |  | 160 | 2016-01-30 |  | In Build Phase
SR_09 | Enhancement | Muthu | Data Recon | Introducing Seq based Comparison in data recon | 2016-01-19 | High |  |  |  | 36 | 2015-01-25 |  | In Build Phase
SR_10 | Enhancement | Dhamo/Gopal | ALL | SQL to Oracle Conversion | 2015-12-18 | Medium |  |  |  | 52 | 2016-01-05 | 2016-01-05 | Completed
SR_11 | Enhancement | Suresh | Hexarule | to Combine “Rule Allocation” and “Process and Updates” into one Tab to avoid 2 step process | 2015-01-15 |  | Simple |  |  | 4 |  |  |  | Pandian's Feedback while doing demo with the Bel;fius
SR_12 | Enhancement | Suresh | Hexarule | Exporting Rules in the XML format | 2015-01-15 |  | Medium |  |  | 8
SR_13 | Enhancement | Suresh | Hexarule | Validate the Hexarule volume Capability:Promised to the customer that this will withstand uptp 8 TB | 2015-01-15 |  | High
SR_14 | Enhancement | Suresh | DMO | capability to load .CSV format data into DMO platform | 2015-01-15 |  | Medium | [6 empty] | Need to discuss with prasad
SR_15 | Enhancement | Suresh | Hexarule | Bulk Updates | 2015-01-15 |  | Medium | [6 empty] | Need to discuss with prasad
SR_16 | Enhancement | Muthu | Profiler | Adding existing reports with Intact reports(Like Pattern Matching reports) and currently it’s been removed | 2015-01-15 |  | Medium |  |  | 8
SR_17 | Enhancement | Muthu | Profiler | Adjust length and width of the Buttons in the Profiling interface | 2015-01-15 |  | Simple |  |  | 1
SR_18 | Enhancement | Muthu | Profiler | Running profiler on Batch mode | 2015-01-15 |  | High |  |  | 25
SR_19 | Enhancement | Muthu | Profiler | Details on who and when the Profiling been done to be listed while checing the reports | 2015-01-15 |  | Medium |  |  | 10
SR_20 | Enhancement | Muthu | Profiler | Defaulting Profiler master dashboard while navigating to report page after profiling | 2015-01-15 |  | Simple |  |  | 1
SR_21 | Enhancement | Muthu | Profiler | Remove Sample from “Sample View Data” of button text | 2015-01-15 |  | Simple |  |  | 0.5
SR_22 | Enhancement | Muthu | Excel File upload Interface | Dynamically crating the table to be loaded from excel file | 2015-01-15 |  | High |  |  | 8
SR_23 | Enhancement | Muthu | Excel File upload Interface | Before loading ,Need to see the sample data to be loaded for the profiling | 2015-01-15 |  | Simple |  |  | 2 |  |  | Completed
SR_24 | Enhancement | Muthu | Excel File upload Interface | There will be feasible option to decide the data type by seeing the data before creating and pushing it for Hexarule | 2015-01-15 |  | High |  |  | 20
SR_25 | Enhancement | Muthu | Excel File upload Interface | Messages on Success /Failure, Progress and number of records processed | 2015-01-15 |  | Medium |  |  | 5